## Read me
Kendis PI Planning template
Free to use and adapt. Shaded rows are examples: overwrite or delete them. From kendis.io/pi-planning-template/
Sheet | Use it for | When
Agenda | Two-day PI Planning agenda with owners and outputs | Fill in 4 to 6 weeks before
Readiness checklist | Everything that must be ready before day one | Start 6 weeks before
Team capacity | Capacity per team per iteration | Week before PI Planning
PI objectives | Team objectives with planned and actual business value | During and after the event
Dependencies | Cross-team dependencies and their status | During the team breakouts
ROAM risks | Risk register with ROAM status and owners | Breakouts and ART risk session
Confidence vote | Fist-of-five vote per team and for the train | End of day two
Retrospective | What to keep, change and try next PI | Last session of day two

## Agenda
Two-day PI Planning agenda
Sample timings. Keep the order, adjust the clock to your time zones.
Day | Start | End | Session | Led by | Output | Materials ready? (Y/N)
1 | 08:00 | 09:00 | Business context | Business Owner or executive | Shared view of business priorities
1 | 09:00 | 10:30 | Product and solution vision | Product Management | Top features for the PI
1 | 10:30 | 11:30 | Architecture vision and development practices | System Architect | Enablers and technical direction
1 | 11:30 | 13:00 | Planning context and lunch | RTE | How the two days work
1 | 13:00 | 16:00 | Team breakouts 1 | Teams | Draft plans, objectives, risks, dependencies
1 | 16:00 | 17:00 | Draft plan review | Teams | Draft plans presented to the train
1 | 17:00 | 18:00 | Management review and problem solving | RTE and Business Owners | Decisions on scope, people, dependencies
2 | 08:00 | 09:00 | Planning adjustments | Business Owners | Changes communicated to all teams
2 | 09:00 | 11:00 | Team breakouts 2 | Teams | Final plans, business value assigned
2 | 11:00 | 13:00 | Final plan review and lunch | Teams | Plans accepted by Business Owners
2 | 13:00 | 14:00 | ART risks | RTE | Risks ROAMed in front of the train
2 | 14:00 | 14:15 | Confidence vote | RTE | Vote per team and for the train
2 | 14:15 | 16:00 | Plan rework, if needed | Teams | Plan the train is confident in
2 | 16:00 | 17:00 | Planning retrospective and next steps | RTE | Improvements for next PI

## Readiness checklist
PI Planning readiness checklist
Tick each item as it is done. Weeks are counted back from day one.
When | Area | Item | Owner | Done (Y/N)
6 weeks | Organisation | Scope agreed: which product and which teams plan together | RTE
6 weeks | Organisation | PI dates, iteration dates and the IP iteration published | RTE
5 weeks | Organisation | Business Owners named, briefed and available for both days | RTE
5 weeks | Logistics | Venue or video platform booked, breakout rooms per team | RTE
4 weeks | Content | Top features ranked and refined with acceptance criteria | Product Management
4 weeks | Content | Architecture vision, enablers and non-functional requirements ready | System Architect
3 weeks | Content | Milestones, fixed dates and external commitments listed | Product Management
2 weeks | Logistics | Planning board set up: teams, iterations, features loaded | RTE
2 weeks | Logistics | Everyone has access to the board and has opened it once | Scrum Masters
1 week | Content | Team capacity per iteration calculated, including leave | Scrum Masters
1 week | Content | Business context briefing prepared | Business Owner
1 week | Logistics | Agenda with time zones and communication channels sent | RTE
1 week | Logistics | Fallback agreed in case a tool or connection fails | RTE

## Team capacity
Team capacity per iteration
Example method: people x available days x focus factor. Use the estimation baseline your teams already agree on.
Team | Iteration | People | Working days | Leave and holiday days | Available days | Focus factor | Capacity (days) | Planned load | Load vs capacity
Team Alpha | Iteration 1 | 6 | 10 | 4 |  | 0.7 |  | 30
Team Alpha | Iteration 2 | 6 | 10 | 0 |  | 0.7 |  | 40
Team Beta | Iteration 1 | 5 | 10 | 2 |  | 0.7 |  | 36

## PI objectives
PI objectives
Business Owners assign planned business value during the event; actual value is scored at the end of the PI.
Team | PI objective | Committed or uncommitted | Linked features | Planned business value (1-10) | Actual business value (1-10) | Achievement %
Team Alpha | Customers can pay with saved cards on web and mobile | Committed | F-101, F-104 | 8 | 7
Team Alpha | Reduce checkout errors by half | Uncommitted | F-110 | 5

## Dependencies
Cross-team dependencies
One row per dependency. Agree the needed-by iteration with both teams.
ID | Needed by team | Provided by team | What is needed | Linked feature or story | Needed by iteration | Owner | Status
D-1 | Team Alpha | Team Beta | Payments API endpoint for saved cards | F-101 | Iteration 2 | Team Beta PO | Committed

## ROAM risks
ROAM risk register
Resolved: no longer a concern. Owned: someone takes responsibility. Accepted: nothing more can be done. Mitigated: a plan reduces the impact.
ID | Risk | Raised by | Impact (1-5) | Likelihood (1-5) | ROAM status | Owner | Action | Due
R-1 | Payment provider sandbox may not be ready before Iteration 2 | Team Alpha | 4 | 3 | Owned | RTE | Escalate to vendor, weekly check | End of Iteration 1

## Confidence vote
Confidence vote (fist of five)
Count the votes for each score. A common working rule: average of 3 or more is accepted; ask everyone who voted 1 or 2 to explain.
Team | Votes of 1 | Votes of 2 | Votes of 3 | Votes of 4 | Votes of 5 | Total votes | Average | Concerns raised
Team Alpha | 0 | 1 | 3 | 4 | 1 |  |  | Sandbox dependency
Whole train

## Retrospective
PI Planning retrospective
Run in the last session of day two. Capture actions with an owner.
Question | Notes | Action | Owner
What went well and should we keep?
What slowed us down or should change?
What should we try at the next PI Planning?
Was preparation enough? What was missing?
How did the tooling and remote setup work?