## Read me
Kendis Scrum of Scrums template
Free to use and adapt. Shaded rows are examples: overwrite or delete them. From kendis.io/scrum-of-scrums-template/
Sheet | Use it for | When
Agenda | A 15-minute Scrum of Scrums agenda | Every meeting
Team updates | Each team answers the same questions before or during the meeting | Every meeting
Impediments | Impediments the teams cannot solve alone, with an owner | Raised any time, reviewed every meeting
Dependencies | Cross-team dependencies and their status | Reviewed every meeting
Action items | Decisions and follow-ups with an owner and a due date | End of every meeting

## Agenda
Scrum of Scrums agenda (15 minutes)
Timebox the meeting. Problem solving happens after it, with only the people needed.
Minute | Item | Who | Output
0 to 1 | Open: review open action items from last time | Facilitator (Scrum Master or RTE) | Actions closed or carried over
1 to 9 | Team updates: impediments, impact on other teams, new dependencies | One representative per team | Updated impediments and dependencies
9 to 13 | Impediments and dependencies that need a decision | Facilitator | Owner and next step for each
13 to 15 | Close: confirm action items and owners | Facilitator | Action list for the next meeting
After | Problem solving with the people involved only | Owners | Resolved or escalated items

## Team updates
Team updates
The three questions follow the Scrum@Scale Guide. Add a short progress note against the sprint or PI goal.
Date | Team | Impediments that put our Sprint Goal or delivery plan at risk | Anything we are doing that may block another team | New dependencies found, or a way to resolve one | Progress against the goal
| Team Alpha | Test environment unavailable since Tuesday | Changing the payments API schema in sprint 3 | Needs Team Beta to update the client by sprint 4 | On track for the sprint goal

## Impediments
Impediment log
One row per impediment that a team cannot solve alone.
ID | Raised | Team | Impediment | Impact | Owner | Next step | Status | Resolved on
I-1 |  | Team Alpha | Test environment unavailable | Blocks testing for 2 stories | Platform lead | Restore environment, confirm by Thursday | Open

## Dependencies
Cross-team dependencies
Agree the needed-by sprint with both teams.
ID | Needed by team | Provided by team | What is needed | Needed by sprint | Status | Notes
D-1 | Team Beta | Team Alpha | Updated payments API client | Sprint 4 | Committed

## Action items
Action items
Close every meeting by confirming owners and due dates.
Date raised | Action | Owner | Due | Done (Y/N)
| Ask platform team for test environment ETA | Facilitator | Next meeting