## Kendis-Checklist-v2.0
| Actions | Completed | Additional Comments
1 | User Management
1.1 | Have you removed "Resync Boards" rights from User Profile | Select Value | Only admin/RTE users should have this right
1.2 | Invited all Users needed to view or edit Kendis | Select Value
1.3 | Have you shared the "Getting Started" inks from Kendis to your team members who are going to use Kendis first time | Select Value | Getting Started link at help.kendis.io
1.4 | Assigned Users to the correct Board Collection | Select Value
2 | Creating Board
2.1 | Each Scrum Master has entered Capacity values for their team sprints | Select Value | In Team area, at Kendis, you can set the value of capcity for each team and sprint
2.2 | Have you set the dates of the sprint | Select Value
2.3 | Have you set the dates of the PI | Select Value
2.4 | Change status of Board from Draft to Start Planning | Select Value
3 | Load Projects
3.1 | Have you loaded all the needed projects at Kendis | Select Value | You can go to Board Settings --> Edit Board Settings --> Projects
3.2 | In case you have made changes to the project like added new status or added new item type, have you updated the loaded project at Kendis | Select Value | You can go to Board Settings --> Edit Board Settings --> Projects --> click on the resync icon
4 | Get Contents from AzureDevOps
4.1 | Have you included only Features in your query | Select Value | Query should only include the features, don't include story item type in the query
4.2 | Did you make sure, you have included features related to your PI only | Select Value
4.3 | Have you selected correct link type between feature and stories | Select Value | If you are using Parent-Child link at AzureDeveOps in then you should select "CHILD" as ink type when asked at the Get Contents from AzureDevOps Screen
4.4 | In case you are not seing your query, have you made sure, your query is saved at the root folder in AzureDevOps | Select Value
5 | Team Mappings at Kendis
5.1 | Have you mapped each team(swimlane) at Kendis to AzureDevOps Teams | Select Value | Selected project
5.2 | Have you mapped all the sprints correctly | Select Value | If you don't map the sprints before the planning and once planning done then you will not be able to move your stories that are at Kendis board to AzureDevOps
5.3 | Have you selected "User Story" as the item type | Select Value | In this area, you should select the User Story item type
5.4 | Have you selected default "Areapath" in case teams have multiple area paths | Select Value | This default area path will be used in case of drag an drop stories to different teams
6 | Test Round
6.1 | Have you fetched a sample feature into Kendis from AzureDevOps | Select Value | You can write a sample query at AzureDevOps where you just include one test feature that has couple of stories
6.2 | Feature is visible at Kendis with the stories | Select Value
6.3 | Edit the feature and change title | Select Value
6.4 | Move a story from the feature to a sprint | Select Value
6.5 | Create a new story under that feature | Select Value | Make sure link type is pre-selected as "Parent", in case you are using "Parent-Child" link
6.6 | Edit the story and change story Points | Select Value | Make sure changes appear in AzureDevOps
6.7 | Now edit the same story in AzureDevOps and update story points | Select Value | Make sure the changes appear in Kendis (to make sure webhook is working)
6.8 | Now edit the same story in AzureDevOps and change sprint to another sprint | Select Value | Make sure the changes appear in Kendis and story is moved to second sprint in same team
6.9 | Create dependency between two cards | Select Value | Make sure dependencies toggle is working by ON/OFF
6.10 | Created Objective and linked to the feature | Select Value
7 | Testing Real-time board
7.1 | Open 2 browser windows, now make a change like edit title of the feature and see it's visible in second tab without refresh | Select Value
7.2 | Create a dependency and see if it's visible in the second tab without refresh | Select Value
7.3 | Change sprint of a story and see if it's visible in second tab | Select Value
PI Planning Checklist
Version: 2.0

## Data-Prep
Select Value
Done
Not Done
Select Value
Worked
Didn't work
Not Understanding